## Schedule
PUBLISHING SCHEDULE
Use the schedule template below to start planning your publishing strategy. Note that the three phases (editorial, production, and marketing) can and should run parallel to each other, and, many of the marketing activities will be ongoing tasks. Play around with the dates provided as an example to get an idea of how long you will need to get everything ready.
TASK OR MILESTONE | DURATION/NOTES | BEGINS | ENDS
EDITORIAL PHASE
Developmental editing | 2 - 6 months | 2021-01-01 | 2021-07-01
Copy editing | 1 - 2 months | 2021-07-01 | 2021-08-01
Proofreading | 2 - 4 weeks | 2021-08-01 | 2021-08-15
PRODUCTION PHASE
Procure ISBNS | 1 week | 2021-07-01 | 2021-07-07
Book design and formatting | 1 month | 2021-08-15 | 2021-09-15
Cover design and formatting | 1 month | 2021-08-15 | 2021-09-15
E-book conversion | 2 weeks | 2021-09-15 | 2021-10-15
Upload to publishing platform | 1 day | 2021-10-30 | 2021-10-30
MARKETING PHASE
Create marketing plan | 1 - 2 weeks | 2021-01-01 | 2021-01-15
Open social media accounts | 1 week | 2021-01-15 | 2021-01-25
Create website | 1 - 2 months | 2021-01-25 | 2021-03-25
Make a list of potential reviewers and contact them | 2 weeks | 2021-01-15 | 2021-01-30
Send out advance review copies* | Ongoing | 2021-08-30 | 2021-09-15
Book launch | 1 day | 2021-10-30 | 2021-10-30
*Advance review copies do not have to be perfect. You can send the first proofs in PDF form to gather testimonials, or even the raw, proofread manuscript if you explain to the reviewers that the design is still in progress.